🧠 STACK PRIORITY (LOCK THIS)

DSA (make/break factor)

Java + Spring Boot

React

System Design

Cloud + Docker (minimum)

🗓️ MONTH 1 (FOUNDATION HARDENING)

DSA (Daily 2.5 hrs)

Target: 120–150 problems

Focus only on interview patterns

Arrays, Strings

HashMap

Sliding Window

Two Pointers

Stack & Queue

👉 Rule:

2 problems/day (medium)

No random solving — pattern based

Java (Daily 1 hr)

Only interview-relevant

Collections (deep)

equals/hashCode

Streams

Optional

Exception handling

Immutability

Thread basics

JavaScript (Daily 45 min)

High ROI topics

Closures

Event loop

this

Promise chaining

Async/await

Debounce / Throttle

🗓️ MONTH 2 (BACKEND + FRONTEND DEPTH)

Spring Boot (Daily 2 hrs)

This must be strong

REST best practices

Pagination

JPA mappings

Transactions

JWT + RBAC

Global exception handling

API versioning

👉 Build 1 strong backend project
(E-commerce / Order / Auth)

React (Daily 2 hrs)

Focus on real patterns

Hooks mastery

Forms

API integration

Memoization

Pagination

Role-based UI

👉 Build Admin Dashboard
(No fancy CSS, logic > UI)

DSA (Daily 2 hrs)

Trees

Binary Search

Recursion

🗓️ MONTH 3 (SYSTEM DESIGN + ADVANCED DSA)

DSA (Daily 2 hrs)

Graphs

Heaps

DP (limited)

Timed mock tests

System Design (Daily 1.5 hrs)

This differentiates you

High-level design

DB schema design

Caching

Rate limiting

API design

👉 Practice designs:

URL Shortener

E-commerce

Notification system

Cloud + Docker (30–45 min/day)

Only essentials

Dockerfile

Docker Compose

AWS EC2 + RDS

Deployment flow

👉 Deploy your project (VERY IMP)

🗓️ MONTH 4 (INTERVIEW MODE 🔥)

Daily Routine:

1 DSA timed problem

1 system design question

Java + Spring revision

Resume Upgrade (CRITICAL)

Your resume should say:

“Designed REST APIs handling X requests/day”

“Reduced API latency by X%”

“Implemented JWT-based auth”

APPLY AGGRESSIVELY (BUT SMART)

Referrals > LinkedIn Easy Apply

Target:

Product companies

Funded startups

FinTech

👉 5 referrals/week minimum

⏱️ DAILY TIME COMMITMENT (REQUIRED)

| Skill | Time |
| --- | --- |
| DSA | 2–2.5 hrs |
| Backend/Frontend | 3–4 hrs |
| System Design | 1–1.5 hrs |
| Revision | 30 min |
| Total | 6–8 hrs/day |